## 0Work_Completion_Browse63729475
| Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse
| !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!!
| Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All
| Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All
| Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All
| From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010
| Page 1 of 4 | Page 1 of 4 | Page 1 of 4 | Page 1 of 4 | Page 1 of 4 | Page 1 of 4 | Page 1 of 4 | Page 1 of 4 | Page 1 of 4 | Page 1 of 4 | Page 1 of 4 | Page 1 of 4 | Page 1 of 4 | Page 1 of 4 | Page 1 of 4
Labour | Contractor | WO_No | Task | Qty | Rate | Amount | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | Approve_Amount | Approve_Date | Balanced | Executed_By
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 100 | 4500 | 45000 | 2017-06-26 | PLINTH | 10 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 80 | 4500 | 36000 | 2017-06-27 | PLINTH | 10 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 10 | 4500 | 4500 | 2017-06-27 | PLINTH | 10 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 1 | 4500 | 450 | 2017-08-17 | PLINTH | 10 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 1 | 4500 | 450 | 2017-08-17 | PLINTH | 10 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 1 | 4500 | 450 | 2017-08-17 | PLINTH | 10 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 1 | 4500 | 450 | 2017-09-18 | PLINTH | 10 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 1 | 4500 | 450 | 2017-09-18 | PLINTH | 10 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 1 | 4500 | 450 | 2017-09-18 | PLINTH | 10 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 0.5 | 4500 | 225 | 2017-09-18 | PLINTH | 10 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 10 | 4500 | 4500 | 2017-05-24 13:12 | PLINTH | 10 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 10 | 4500 | 4500 | 2017-05-24 13:13 | PLINTH | 10 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 100 | 4500 | 45000 | 2017-05-24 13:19 | PLINTH | 10 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 0 | 4500 | 0 | 2017-05-08 15:36 | PLINTH | 10 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 16 | 4500 | 7200 | 2017-05-24 13:07 | PLINTH | 10 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 1000 | 4500 | 450000 | 2017-05-24 13:07 | PLINTH | 10 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 100 | 4500 | 45000 | 2017-05-24 13:10 | PLINTH | 10 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 1 | 4500 | 450 | 2017-11-09 | PLINTH | 10 | Ok |  |  |  |  | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 1 | 4500 | 450 | 2017-11-09 | PLINTH | 10 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 0.5 | 4500 | 225 | 2017-11-17 | PLINTH | 10 | Rem |  |  |  |  | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 1 | 4500 | 450 | 2018-02-06 | PLINTH | 10 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 1 | 4500 | 450 | 2018-02-06 | PLINTH | 10 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 2 | 4500 | 900 | 2018-03-05 | PLINTH | 10 | Test |  |  |  |  | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 4000 | 4500 | 1800000 | 2018-03-05 | PLINTH | 10 | Partial completed |  |  |  |  | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 23 | 4500 | 10350 | 2018-03-20 | PLINTH | 10 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Brick work working | 01 ABHIJIT CONSTRUCTION | 1 | BrickWork Brickwork | 4994354 | 4500 | 2247459300 | 2019-01-04 10:46 | PLINTH | 10 | Entry from Task Closure screen |  |  |  |  | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 10 | 11 | 27.5 | 2016-08-08 13:10 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 10 | 11 | 27.5 | 2016-08-08 14:14 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 15:37 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 15:38 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 15:49 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 15:49 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 15:40 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 15:47 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 16:05 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 16:07 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 16:08 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 16:10 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 15:57 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 15:51 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 15:51 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 15:57 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 16:10 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 16:08 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 16:07 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 16:05 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 15:47 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 15:40 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 15:49 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 15:49 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 15:38 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 0 | 11 | 0 | 2016-11-19 15:37 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 10 | BBM 115MM (CM 1:4)_21791 | 10 | 11 | 82.5 | 2016-08-08 14:14 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Internal Plaster | !!Test Contractor | 107 | 01 Internal Plaster_22492 | 1 | 100 | 100 | 2017-10-11 12:49 | Test payment schdule | 100 | [5 empty] | !!Test Contractor
Internal Plaster | !!Test Contractor | 107 | 01 Internal Plaster_22492 | 1 | 100 | 100 | 2018-02-28 14:02 | Test payment schdule | 100 | [5 empty] | !!Test Contractor
Internal Plaster | !!Test Contractor | 107 | 01 Internal Plaster_22492 | 0.1 | 100 | 10 | 2018-03-05 12:25 | Test payment schdule | 100 | [5 empty] | !!Test Contractor
Internal Plaster | !!Test Contractor | 107 | 01 Internal Plaster_22492 | 2 | 100 | 200 | 2018-01-22 14:12 | Test payment schdule | 100 | [5 empty] | !!Test Contractor
Internal Plaster | !!Test Contractor | 107 | 01 Internal Plaster_22492 | 1 | 100 | 100 | 2017-11-01 | Test payment schdule | 100 | [5 empty] | !!Test Contractor
Internal Plaster | !!Test Contractor | 107 | 01 Internal Plaster_22492 | 0.5 | 100 | 50 | 2017-11-23 | Test payment schdule | 100 | [5 empty] | !!Test Contractor
Internal Plaster | !!Test Contractor | 107 | 01 Internal Plaster_22492 | 4.4 | 100 | 440 | 2018-04-05 10:18 | Test payment schdule | 100 | [5 empty] | !!Test Contractor
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 40 | 15 | 150 | 2016-08-09 11:30 | While generate WO | 25 |  | 542 | 600 |  | -450 | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 20 | 15 | 75 | 2016-08-10 13:23 | While generate WO | 25 |  | 543 | 300 |  | -225 | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:37 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:38 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:49 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:49 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:40 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:47 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 16:05 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 16:07 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 16:08 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:57 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:51 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:51 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:57 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 16:08 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 16:07 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 16:05 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:47 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:40 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:49 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:49 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:38 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:37 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 20 | 15 | 225 | 2016-08-10 13:23 | On Completion | 75 |  | 543 | 300 |  | -75 | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 11 | RCC RCC COLUMN M20_21941 | 40 | 15 | 450 | 2016-08-09 11:30 | On Completion | 75 |  | 542 | 600 |  | -150 | 01 ABHIJIT CONSTRUCTION
Brick work working | 0001A_cont | 110 | BrickWork Brickwork_22494 | 0 | 16 | 0 | 2018-04-05 09:51 | Test payment schdule | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Brick work working | 0001A_cont | 110 | BrickWork Brickwork_22494 | 0 | 16 | 0 | 2018-04-05 10:11 | Test payment schdule | 100 | [5 empty] | A-testing
Brick work working | 0001A_cont | 110 | BrickWork Brickwork_22494 | 0 | 16 | 0 | 2018-04-05 10:14 | Test payment schdule | 100 | [5 empty] | Aanand Pune
Brick work working | 0001A_cont | 110 | BrickWork Brickwork_22494 | 0 | 16 | 0 | 2018-04-05 10:16 | Test payment schdule | 100 | [5 empty] | BVS QUALITY SYSTEM
Brick work working | 0001A_cont | 110 | BrickWork Brickwork_22494 | 109 | 16 | 1744 | 2018-01-22 17:33 | Test payment schdule | 100 | [5 empty] | !!Test Contractor
Brick work working | 0001A_cont | 110 | BrickWork Brickwork_22494 | 11 | 16 | 176 | 2017-11-17 16:26 | Test payment schdule | 100 | [5 empty] | !!Test Contractor
Brick work working | 0001A_cont | 110 | BrickWork Brickwork_22494 | 0 | 16 | 0 | 2018-03-17 18:33 | Test payment schdule | 100 | [5 empty] | !!Test Contractor
Brick work working | 0001A_cont | 110 | BrickWork Brickwork_22494 | 0 | 16 | 0 | 2018-02-28 14:00 | Test payment schdule | 100 | [5 empty] | !!Test Contractor
Brick work working | 0001A_cont | 110 | BrickWork Brickwork_22494 | 0 | 16 | 0 | 2018-05-16 12:12 | Test payment schdule | 100 | [5 empty] | !!Test Contractor
Brick work working | 0001A_cont | 110 | BrickWork Brickwork_22494 | 0 | 16 | 0 | 2018-05-16 12:12 | Test payment schdule | 100 | [5 empty] | !!Test Contractor
All LAbour | 01 ABHIJIT CONSTRUCTION | 12 | RCC RCC COLUMN M20_21941 | 40 | 15 | 150 | 2016-08-10 15:30 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 12 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:37 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 12 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:38 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 12 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:49 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 12 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:49 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 12 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:40 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 12 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:47 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 12 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 16:05 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 12 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 16:07 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 12 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 16:08 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 12 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:57 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 12 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:51 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 12 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:51 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 12 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:57 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 12 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 16:09 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 12 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 16:07 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 12 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 16:05 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 12 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:47 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 12 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:40 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 12 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:49 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 12 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:49 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 12 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:38 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 12 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:37 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 12 | RCC RCC COLUMN M20_21941 | 40 | 15 | 450 | 2016-08-10 15:30 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
<LABOUR FOR RCC SLAB AND BEAMS> - R.Ft | !!Test Contractor | 123 | 2ND SLAB RCC PARDI M20_102811 | 10 | 1050 | 10500 | 2018-05-16 12:20 | SAMPLE | 100 |  | 685 | 0 |  | 10500 | !!Test Contractor
<LABOUR FOR RCC SLAB AND BEAMS> - R.Ft | !!Test Contractor | 123 | 2ND SLAB RCC PARDI M20_102811 | 10 | 1050 | 10500 | 2018-05-16 12:20 | SAMPLE | 100 | [5 empty] | !!Test Contractor
<LABOUR FOR RCC SLAB AND BEAMS> - R.Ft | !!Test Contractor | 123 | 2ND SLAB RCC PARDI M20_102811 | 10 | 1050 | 10500 | 2018-05-16 12:20 | SAMPLE | 100 | [5 empty] | !!Test Contractor
<LABOUR FOR RCC SLAB AND BEAMS> - R.Ft | !!Test Contractor | 123 | 2ND SLAB RCC PARDI M20_102811 | 10 | 1050 | 10500 | 2018-05-16 12:57 | SAMPLE | 100 | [5 empty] | !!Test Contractor
<LABOUR FOR RCC SLAB AND BEAMS> - R.Ft | !!Test Contractor | 123 | 2ND SLAB RCC PARDI M20_102811 | 10 | 1050 | 10500 | 2018-05-16 12:57 | SAMPLE | 100 | [5 empty] | !!Test Contractor
<LABOUR FOR RCC SLAB AND BEAMS> - R.Ft | !!Test Contractor | 123 | 2ND SLAB RCC PARDI M20_102811 | 10 | 1050 | 10500 | 2018-05-16 12:57 | SAMPLE | 100 | [5 empty] | !!Test Contractor
<LABOUR FOR RCC SLAB AND BEAMS> - R.Ft | !!Test Contractor | 123 | 2ND SLAB RCC PARDI M20_102811 | 5 | 1050 | 5250 | 2018-05-16 16:56 | SAMPLE | 100 | [5 empty] | !!Test Contractor
<LABOUR FOR RCC SLAB AND BEAMS> - R.Ft | !!Test Contractor | 123 | 2ND SLAB RCC PARDI M20_102811 | 3 | 1050 | 3150 | 2018-05-16 17:16 | SAMPLE | 100 | [5 empty] | !!Test Contractor
A_Swa | !!Test Contractor | 124 | SAMPLE BUILDING 01 Internal Plaster_102787 | 5 | 2000 | 6000 | 2018-05-21 | 60part | 60 |  | 684 | 6000 |  | 0 | !!Test Contractor
A_Swa | !!Test Contractor | 124 | SAMPLE BUILDING 01 Internal Plaster_102787 | 5 | 2000 | 4000 | 2018-05-21 | bal.part | 40 |  | 688 | 4000 |  | 0 | !!Test Contractor
<LABOUR FOR RCC SLAB AND BEAMS> - R.Ft | !!Test Contractor | 125 | BELOW GROUND RCC PARDI M20_102804 | 5 | 1050 | 1837.5 | 2018-06-20 15:55 | Concreting Work | 35 | [5 empty] | !!Test Contractor
<LABOUR FOR RCC SLAB AND BEAMS> - R.Ft | !!Test Contractor | 125 | BELOW GROUND RCC PARDI M20_102804 | 0 | 1050 | 0 | 2018-06-20 17:12 | Concreting Work | 35 | [5 empty] | !!Test Contractor
<LABOUR FOR RCC SLAB AND BEAMS> - R.Ft | !!Test Contractor | 125 | BELOW GROUND RCC PARDI M20_102804 | 45 | 1050 | 16537.5 | 2019-02-13 | Concreting Work | 35 | [5 empty] | !!Test Contractor
LABOUR FOR RCC COLUMN WORK | !!Test Contractor | 128 | 1ST SLAB RCC PARDI M20_102807 | 5 | 100 | 500 | 2018-06-20 17:17 | EXCAVATION FOR ROAD | 100 | [5 empty] | !!Test Contractor
LABOUR FOR RCC COLUMN WORK | !!Test Contractor | 128 | 1ST SLAB RCC PARDI M20_102807 | 10 | 100 | 1000 | 2018-06-20 17:30 | EXCAVATION FOR ROAD | 100 | [5 empty] | !!Test Contractor
LABOUR FOR RCC COLUMN WORK | !!Test Contractor | 128 | 1ST SLAB RCC PARDI M20_102807 | 10 | 100 | 1000 | 2018-06-20 17:47 | EXCAVATION FOR ROAD | 100 | [5 empty] | !!Test Contractor
LABOUR FOR RCC COLUMN WORK | !!Test Contractor | 128 | 1ST SLAB RCC PARDI M20_102807 | 5 | 100 | 500 | 2018-06-20 17:47 | EXCAVATION FOR ROAD | 100 | [5 empty] | !!Test Contractor
LABOUR FOR RCC COLUMN WORK | !!Test Contractor | 128 | 1ST SLAB RCC PARDI M20_102807 | 15 | 100 | 1500 | 2018-06-21 15:30 | EXCAVATION FOR ROAD | 100 |  | 694 | 1500 |  | 0 | !!Test Contractor
LABOUR FOR RCC COLUMN WORK | !!Test Contractor | 128 | 1ST SLAB RCC PARDI M20_102807 | 100 | 100 | 10000 | 2018-07-02 11:58 | EXCAVATION FOR ROAD | 100 | [5 empty] | !!Test Contractor
LABOUR FOR RCC COLUMN WORK | !!Test Contractor | 128 | 1ST SLAB RCC PARDI M20_102807 | 0 | 100 | 0 | 2018-07-02 11:58 | EXCAVATION FOR ROAD | 100 | [5 empty] | !!Test Contractor
LABOUR FOR RCC COLUMN WORK | !!Test Contractor | 128 | 1ST SLAB RCC PARDI M20_102807 | 10 | 100 | 1000 | 2018-06-20 16:56 | EXCAVATION FOR ROAD | 100 | [5 empty] | !!Test Contractor
LABOUR FOR RCC COLUMN WORK | !!Test Contractor | 128 | 1ST SLAB RCC PARDI M20_102807 | 2 | 100 | 200 | 2018-06-20 17:12 | EXCAVATION FOR ROAD | 100 | [5 empty] | !!Test Contractor
LABOUR FOR RCC COLUMN WORK | !!Test Contractor | 128 | 1ST SLAB RCC PARDI M20_102807 | 14 | 100 | 1400 | 2018-07-02 16:25 | EXCAVATION FOR ROAD | 100 | [5 empty] | !!Test Contractor
LABOUR FOR RCC COLUMN WORK | !!Test Contractor | 128 | 1ST SLAB RCC PARDI M20_102807 | 21 | 100 | 2100 | 2018-07-02 16:27 | EXCAVATION FOR ROAD | 100 | [5 empty] | !!Test Contractor
LABOUR FOR RCC COLUMN WORK | !!Test Contractor | 128 | 1ST SLAB RCC PARDI M20_102807 | 12 | 100 | 1200 | 2018-07-02 16:34 | EXCAVATION FOR ROAD | 100 | [5 empty] | !!Test Contractor
LABOUR FOR RCC COLUMN WORK | !!Test Contractor | 128 | 1ST SLAB RCC PARDI M20_102807 | 32 | 100 | 3200 | 2018-07-02 16:52 | EXCAVATION FOR ROAD | 100 | [5 empty] | !!Test Contractor
LABOUR FOR RCC COLUMN WORK | !!Test Contractor | 128 | 1ST SLAB RCC PARDI M20_102807 | 25 | 100 | 2500 | 2018-06-12 11:03 | EXCAVATION FOR ROAD | 100 |  | 687 | 2500 |  | 0 | !!Test Contractor
All LAbour | 01 ABHIJIT CONSTRUCTION | 13 | RCC RCC COLUMN M20_21941 | 100 | 15 | 375 | 2016-08-10 17:30 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 13 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:37 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 13 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:38 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 13 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:49 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 13 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:49 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 13 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:40 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 13 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:47 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 13 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 16:05 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 13 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 16:07 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 13 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 16:09 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 13 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:57 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 13 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:51 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 13 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:51 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 13 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:57 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 13 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 16:09 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 13 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 16:07 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 13 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 16:05 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 13 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:47 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 13 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:40 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 13 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:49 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 13 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:49 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 13 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:38 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 13 | RCC RCC COLUMN M20_21941 | 0 | 15 | 0 | 2016-11-19 15:37 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 13 | RCC RCC COLUMN M20_21941 | 100 | 15 | 1125 | 2016-08-10 17:30 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | BBM 115MM (CM 1:4)_21791 | 10 | 250 | 625 | 2016-08-16 16:59 | While generate WO | 25 |  | 575 | 52500 |  | -51875 | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | BBM 115MM (CM 1:4)_21791 | 0 | 250 | 0 | 2016-11-19 15:37 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | BBM 115MM (CM 1:4)_21791 | 0 | 250 | 0 | 2016-11-19 15:38 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | BBM 115MM (CM 1:4)_21791 | 0 | 250 | 0 | 2016-11-19 15:49 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | BBM 115MM (CM 1:4)_21791 | 0 | 250 | 0 | 2016-11-19 15:49 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | BBM 115MM (CM 1:4)_21791 | 0 | 250 | 0 | 2016-11-19 15:40 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | BBM 115MM (CM 1:4)_21791 | 0 | 250 | 0 | 2016-11-19 15:47 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | BBM 115MM (CM 1:4)_21791 | 0 | 250 | 0 | 2016-11-19 16:05 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | BBM 115MM (CM 1:4)_21791 | 0 | 250 | 0 | 2016-11-19 15:57 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | BBM 115MM (CM 1:4)_21791 | 0 | 250 | 0 | 2016-11-19 15:51 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | BBM 115MM (CM 1:4)_21791 | 0 | 250 | 0 | 2016-11-19 15:51 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | BBM 115MM (CM 1:4)_21791 | 0 | 250 | 0 | 2016-11-19 15:57 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | BBM 115MM (CM 1:4)_21791 | 0 | 250 | 0 | 2016-11-19 16:05 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | BBM 115MM (CM 1:4)_21791 | 0 | 250 | 0 | 2016-11-19 15:47 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | BBM 115MM (CM 1:4)_21791 | 0 | 250 | 0 | 2016-11-19 15:40 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | BBM 115MM (CM 1:4)_21791 | 0 | 250 | 0 | 2016-11-19 15:49 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | BBM 115MM (CM 1:4)_21791 | 0 | 250 | 0 | 2016-11-19 15:49 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | BBM 115MM (CM 1:4)_21791 | 0 | 250 | 0 | 2016-11-19 15:38 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | BBM 115MM (CM 1:4)_21791 | 0 | 250 | 0 | 2016-11-19 15:37 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | BBM 115MM (CM 1:4)_21791 | 10 | 250 | 1875 | 2016-08-16 16:59 | On Completion | 75 |  | 575 | 52500 |  | -50625 | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | For Account Linking BBM 115MM (CM 1:4)_21793 | 200 | 250 | 12500 | 2016-08-16 17:06 | While generate WO | 25 |  | 575 | 52500 |  | -40000 | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 250 | 0 | 2016-11-19 15:37 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 250 | 0 | 2016-11-19 15:38 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 250 | 0 | 2016-11-19 15:49 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 250 | 0 | 2016-11-19 15:49 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 250 | 0 | 2016-11-19 15:40 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 250 | 0 | 2016-11-19 15:47 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 250 | 0 | 2016-11-19 16:05 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 14 | For Account Linking BBM 115MM (CM 1:4)_21793 | 0 | 250 | 0 | 2016-11-19 15:57 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION