## 3Work_Completion_Browse63729475
| Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse | Work Completion Browse
| !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!! | !! Kanix Residency !!!
| Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All | Labour : All
| Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All | Contractor : All
| Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All | Executed By : All
| From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010 | From Date : 04/06/2010 To date: 04/06/2010
| Page 4 of 4 | Page 4 of 4 | Page 4 of 4 | Page 4 of 4 | Page 4 of 4 | Page 4 of 4 | Page 4 of 4 | Page 4 of 4 | Page 4 of 4 | Page 4 of 4 | Page 4 of 4 | Page 4 of 4 | Page 4 of 4 | Page 4 of 4 | Page 4 of 4
Labour | Contractor | WO_No | Task | Qty | Rate | Amount | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | Approve_Amount | Approve_Date | Balanced | Executed_By
BBM Labour Work | AA Contractors | 4 | BBM 115MM (CM 1:4)_21791 | 0 | 1000 | 0 | 2016-11-19 15:51 | Full Completion Payment 100 | 100 | [5 empty] | AA Contractors
BBM Labour Work | AA Contractors | 4 | BBM 115MM (CM 1:4)_21791 | 0 | 1000 | 0 | 2016-11-19 15:52 | Full Completion Payment 100 | 100 | [5 empty] | AA Contractors
BBM Labour Work | AA Contractors | 4 | BBM 115MM (CM 1:4)_21791 | 0 | 1000 | 0 | 2016-11-19 16:05 | Full Completion Payment 100 | 100 | [5 empty] | AA Contractors
BBM Labour Work | AA Contractors | 4 | BBM 115MM (CM 1:4)_21791 | 1.1234 | 1000 | 1123.4 | 2017-03-22 | Full Completion Payment 100 | 100 |  | 703 | 1123.4 |  | 0 | AA Contractors
All LAbour | 01 ABHIJIT CONSTRUCTION | 40 | RCC RCC COLUMN M20_21941 | 1 | 6667 | 1666.75 | 2016-09-17 10:07 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 41 | RCC RCC COLUMN M20_21941 | 1 | 6667 | 1666.75 | 2016-09-17 10:17 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 42 | RCC RCC COLUMN M20_21941 | 1.5 | 6667 | 2500.125 | 2016-09-17 10:33 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 43 | RCC RCC COLUMN M20_21941 | 1.5 | 6667 | 2500.125 | 2016-09-17 10:53 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 44 | RCC RCC COLUMN M20_21941 | 1 | 6667 | 1666.75 | 2016-09-17 10:59 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 49 | RCC RCC COLUMN M20_21941 | 2.5 | 6667 | 8333.75 | 2016-09-17 17:31 | 50% Complete | 50 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 49 | RCC RCC COLUMN M20_21941 | 2.5 | 6667 | 8333.75 | 2016-09-17 17:31 | 100%Complete | 50 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 51 | RCC RCC COLUMN M20_21941 | 0.2 | 6667 | 333.35 | 2016-09-27 16:45 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 51 | RCC RCC COLUMN M20_21941 | 0.2 | 6667 | 1000.05 | 2016-09-27 16:45 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 52 | RCC RCC COLUMN M20_21941 | 50 | 300 | 3750 | 2016-09-30 10:50 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 52 | RCC RCC COLUMN M20_21941 | 50 | 300 | 11250 | 2016-09-30 10:50 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 52 | RCC RCC COLUMN M20_21941 | 25 | 50000 | 312500 | 2016-09-30 10:50 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 52 | RCC RCC COLUMN M20_21941 | 25 | 50000 | 937500 | 2016-09-30 10:50 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 54 | First Floor BBM 115MM (CM 1:4)_22251 | 10000 | 250 | 2500000 | 2017-02-04 | As per work Completion | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 56 | First Floor BBM 115MM (CM 1:4)_22252 | 5 | 4500 | 5625 | 2018-12-24 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Internal Plaster | 01 ABHIJIT CONSTRUCTION | 57 | 01 Internal Plaster_17658 | 90.1 | 100 | 2252.5 | 2016-10-27 14:48 | While generate WO | 25 | [5 empty] | 01 ABHIJIT CONSTRUCTION
Internal Plaster | 01 ABHIJIT CONSTRUCTION | 57 | 01 Internal Plaster_17658 | 90.1 | 100 | 6757.5 | 2016-10-27 14:48 | On Completion | 75 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | !!Test Contractor | 59 | Test Group RCC Pardi M20_22077 | 1 | 100 | 25 | 2018-04-05 10:46 | While generate WO | 25 |  | 682 | 25 |  | 0 | !!Test Contractor
All LAbour | !!Test Contractor | 59 | Test Group RCC Pardi M20_22077 | 2 | 100 | 50 | 2018-12-04 | While generate WO | 25 | [5 empty] | !!Test Contractor
All LAbour | !!Test Contractor | 59 | Test Group RCC Pardi M20_22077 | 7 | 100 | 175 | 2019-02-11 | While generate WO | 25 | [5 empty] | !!Test Contractor
All LAbour | 01 ABHIJIT CONSTRUCTION | 6 | RCC RCC COLUMN M20_21941 | 125 | 50000 | 6250000 | 2016-08-01 | Total | 100 |  | 502 | 6250000 | 2016-08-04 21:02 | 0 | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 6 | RCC RCC COLUMN M20_21941 | 25 | 50000 | 1250000 | 2016-08-01 | Total | 100 |  | 503 | 1250000 | 2019-10-11 12:26 | 0 | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 6 | RCC RCC COLUMN M20_21941 | 37.5 | 50000 | 1875000 | 2016-08-01 | Total | 100 |  | 504 | 1875000 |  | 0 | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 6 | RCC RCC COLUMN M20_21941 | 12.5 | 50000 | 625000 | 2016-08-01 | Total | 100 |  | 505 | 625000 |  | 0 | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 6 | RCC RCC COLUMN M20_21941 | 12.5 | 50000 | 625000 | 2016-08-01 | Total | 100 |  | 507 | 625000 | 2017-09-04 17:54 | 0 | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 6 | RCC RCC COLUMN M20_21941 | 25 | 50000 | 1250000 | 2016-08-01 | Total | 100 |  | 506 | 1250000 | 2016-08-05 12:00 | 0 | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | !!Test Contractor | 60 | First Floor BBM 115MM (CM 1:4)_22496 | 1 | 500 | 500 | 2017-07-01 | sasas | 100 |  | 680 | 500 |  | 0 | !!Test Contractor
BBM Labour Work | !!Test Contractor | 60 | First Floor BBM 115MM (CM 1:4)_22496 | 1 | 500 | 500 | 2018-04-03 12:42 | sasas | 100 |  | 689 | 5500 |  | -5000 | !!Test Contractor
BBM Labour Work | !!Test Contractor | 60 | First Floor BBM 115MM (CM 1:4)_22496 | 10 | 500 | 5000 | 2017-03-22 10:37 | sasas | 100 |  | 689 | 5500 |  | -500 | !!Test Contractor
BBM Labour Work | Test Contracor for Work Order Raise | 65 | First Floor BBM 115MM (CM 1:4)_22253 | 100 | 1000 | 100000 | 2018-04-05 16:03 | EXCAVATION IN HARD ROCK | 100 | [5 empty] | 01_TRAINING CONTRACTOR
BBM Labour Work | Test Contracor for Work Order Raise | 65 | First Floor BBM 115MM (CM 1:4)_22253 | 10 | 1000 | 10000 | 2017-07-03 | EXCAVATION IN HARD ROCK | 100 | [5 empty] | Test Contracor for Work Order Raise
BBM Labour Work | Test Contracor for Work Order Raise | 65 | First Floor BBM 115MM (CM 1:4)_22253 | 200 | 1000 | 200000 | 2016-11-24 | EXCAVATION IN HARD ROCK | 100 | sd sdfasdfsdf |  |  |  |  | Test Contracor for Work Order Raise
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 68 | First Floor BBM 115MM (CM 1:4)_22253 | 25 | 250 | 6250 | 2017-07-01 | As per work Completion | 100 |  | 808 | 6250 |  | 0 | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 68 | First Floor BBM 115MM (CM 1:4)_22253 | 65 | 250 | 16250 | 2017-07-01 | As per work Completion | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
BBM Labour Work | 01 ABHIJIT CONSTRUCTION | 68 | First Floor BBM 115MM (CM 1:4)_22253 | 5 | 250 | 1250 | 2017-07-01 17:15 | As per work Completion | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 7 | RCC RCC COLUMN M20_21941 | 150 | 6667 | 1000050 | 2010-08-01 | Total | 100 |  | 508 | 1000050 | 2016-08-05 12:26 | 0 | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 7 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 15:37 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 7 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 15:38 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 7 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 15:49 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 7 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 15:40 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 7 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 15:47 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 7 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 16:05 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 7 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 16:07 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 7 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 16:07 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 7 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 16:09 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 7 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 16:18 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 7 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 15:52 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 7 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 15:51 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 7 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 16:18 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | !!Test Contractor | 70 | Test Group RCC Pardi M20_22077 | 10 | 100 | 930 | 2016-12-01 10:20 | AGAIN COMPLETION OF WORK | 93 |  | 683 | 930 |  | 0 | !!Test Contractor
All LAbour | !!Test Contractor | 70 | Test Group RCC Pardi M20_22077 | 10 | 100 | 70 | 2016-12-01 10:20 | RETENTION | 7 |  | 690 | 70 |  | 0 | !!Test Contractor
BBM Labour Work | !!Test Contractor | 75 | First Floor BBM 115MM (CM 1:4)_22253 | 10 | 500 | 5000 | 2016-12-15 17:10 | 100% Comkp | 100 | [5 empty] | !!Test Contractor
BBM Labour Work | !!Test Contractor | 75 | First Floor BBM 115MM (CM 1:4)_22253 | 10 | 500 | 5000 | 2018-04-05 10:47 | 100% Comkp | 100 | [5 empty] | !!Test Contractor
BBM Labour Work | !!Test Contractor | 75 | First Floor BBM 115MM (CM 1:4)_22253 | 15 | 500 | 7500 | 2018-04-05 10:56 | 100% Comkp | 100 | [5 empty] | 1.SAMPLE TO CHECK
BBM Labour Work | !!Test Contractor | 75 | First Floor BBM 115MM (CM 1:4)_22253 | 5 | 500 | 2500 | 2018-04-05 11:06 | 100% Comkp | 100 | [5 empty] | !!Test Contractor
BBM Labour Work | !!Test Contractor | 75 | First Floor BBM 115MM (CM 1:4)_22253 | 5 | 500 | 2500 | 2018-04-05 11:06 | 100% Comkp | 100 | [5 empty] | !!Test Contractor
BBM Labour Work | !!Test Contractor | 75 | First Floor BBM 115MM (CM 1:4)_22253 | 3 | 500 | 1500 | 2018-04-05 11:07 | 100% Comkp | 100 | [5 empty] | !!Test Contractor
BBM Labour Work | !!Test Contractor | 75 | First Floor BBM 115MM (CM 1:4)_22253 | 2 | 500 | 1000 | 2018-04-05 11:08 | 100% Comkp | 100 | [5 empty] | !!Test Contractor
BBM Labour Work | !!Test Contractor | 75 | First Floor BBM 115MM (CM 1:4)_22253 | 10 | 500 | 5000 | 2018-04-05 | 100% Comkp | 100 | [5 empty] | AA Contractors
BBM Labour Work | !!Test Contractor | 75 | First Floor BBM 115MM (CM 1:4)_22253 | 5 | 500 | 2500 | 2018-04-05 14:20 | 100% Comkp | 100 | [5 empty] | 3 SAMPLE
All LAbour | 01 ABHIJIT CONSTRUCTION | 8 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 16:18 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 8 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 15:51 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 8 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 15:52 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 8 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 16:18 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 8 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 16:09 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 8 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 16:07 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 8 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 16:07 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 8 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 16:05 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 8 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 15:47 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 8 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 15:40 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 8 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 15:49 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 8 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 15:38 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 8 | RCC RCC COLUMN M20_21941 | 0 | 6667 | 0 | 2016-11-19 15:37 | Total | 100 | [5 empty] | 01 ABHIJIT CONSTRUCTION
All LAbour | 01 ABHIJIT CONSTRUCTION | 8 | RCC RCC COLUMN M20_21941 | 150 | 6667 | 1000050 | 2010-08-01 | Total | 100 |  | 509 | 1000050 |  | 0 | 01 ABHIJIT CONSTRUCTION
RCC R/F WORK | !!Test Contractor | 83 | Test Group R/F STEEL_22003 | 20 | 20 | 400 | 2019-01-03 15:44 | Test payment schdule | 100 | Entry from Task Closure screen |  |  |  |  | !!Test Contractor
BBM Labour Work | ARMAN ENTERPRISES | 95 | First Floor BBM 115MM (CM 1:4)_22496 | 10 | 250 | 625 | 2017-03-20 18:30 | SLAB PIPING | 25 | [5 empty] | ARMAN ENTERPRISES
BBM Labour Work | ARMAN ENTERPRISES | 95 | First Floor BBM 115MM (CM 1:4)_22496 | 10 | 250 | 250 | 2017-03-22 10:42 | TESTING | 10 | [5 empty] | ARMAN ENTERPRISES
RCC R/F WORK | !!Test Contractor | 96 | Test Group R/F STEEL_22003 | 20 | 11 | 220 | 2019-01-03 15:44 | Full Completion Payment 100 | 100 | Entry from Task Closure screen |  |  |  |  | !!Test Contractor
RCC R/F WORK | !!Test Contractor | 96 | Test Group R/F STEEL_22003 | 20 | 11 | 220 | 2019-01-03 15:44 | Full Completion Payment 100 | 100 | Entry from Task Closure screen |  |  |  |  | !!Test Contractor
All LAbour | !!Test Contractor | 98 | CEMENT Cement Work_74539 | 10 | 2000 | 20000 | 2018-12-04 13:32 | Test payment schdule | 100 | [5 empty] | !!Test Contractor
All LAbour | !!Test Contractor | 98 | CEMENT Cement Work_74539 | 10 | 2000 | 20000 | 2018-12-04 14:42 | Test payment schdule | 100 | [5 empty] | !!Test Contractor